## Pain Point Matrix
ID | Pain point | Domain | Stakeholder layer | Stakeholder evidence | Affected roles | Root cause | Business impact | Current workaround | Recommended SKG / TSF response | Priority | Time horizon | Suggested owner | Success metric | Source basis | Status
P01 | Semantic portfolio is hard to navigate | Adoption and communication | Standards and Innovation | Jean-Charles Leclerc: portfolio needs visible business outcomes; archive notes say management cannot navigate what exists. | TSF sponsor, data governance, management sponsors | Semantic work is spread across standards, domains, tooling, and pilots without a business-facing registry. | Sponsors struggle to explain what TSF contains, what is reusable, and why it matters now. | Knowledge remains in expert heads, technical artifacts, and scattered project files. | Create a TSF portfolio registry grouped by business domain, use case, consuming platform, semantic assets, maturity level, and owner. | High | 0-30 days | TSF semantic authority with OneTech data governance | Registry created; 100% of priority LifeX semantic assets mapped to owner, use case, and platform consumer. | Stakeholder perspective summary; archive interview findings. | Open
P02 | Management value is still abstract | Business value and ROI | Standards and Innovation | Benoit Guillermou: management needs concrete examples, scoped deliverables, and reusable materials. | Management sponsors, data officers, platform leads | The semantic message is technically sound but not packaged as decision impact, time saved, risk reduced, or reusable evidence. | Ontology can be perceived as academic or optional, which slows funding and adoption. | Decks explain concepts but need tighter before / after evidence for business users. | Anchor communication around LifeX decision questions, value loops, and validation metrics rather than ontology theory. | High | 0-30 days | OneTech data governance and communication kit owner | Executive deck and one-pager include three LifeX decision questions and three measurable value loops. | Stakeholder perspective summary; executive deck narrative. | Open
P03 | No shared decision framework for when to use SKG | Use case selection | All layers | Archive identifies no decision framework; stakeholders need criteria for ontology versus BI, catalog, RAG, or property graph. | Business owners, architects, data product teams, platform teams | Teams lack a simple gate for fragmented data, cross-team coordination, auditability, standards, and long-term reuse. | Risk of over-engineering simple reporting cases and under-engineering mission-critical semantic cases. | Use case choices are made by local preference, available tooling, or vendor narrative. | Use a 5-question gate: cross-system decision, standards traceability, business impact, reuse over time, vendor-lock-in risk. | High | 0-30 days | Data architecture and TSF semantic authority | Decision framework applied to LifeX and at least three candidate use cases. | Archive executive findings; executive deck decision framework. | Open
P04 | TSF is not wired into the LifeX operational workflow | Operational integration | Operations and Business | Julien Campan: LifeX field evidence flows through local tools; summary frames LifeX as the clearest proof point. | LifeX asset manager, inspectors, operations planners, investment reviewers | Semantic models exist beside the workflow instead of being consumed by the weekly decision cycle. | Field evidence does not become reusable decision intelligence for CAPEX, OPEX, risk, and schedule updates. | Inspection photos, Alteryx, Power BI, Excel, and management memos remain loosely connected. | Create the LifeX semantic data product linking observations, equipment classes, documents, work orders, risk, cost, and decision rationale. | Critical | 0-60 days | LifeX owner with TSF and platform teams | First LifeX decision package traces observation -> concept -> source evidence -> risk / cost impact -> recommendation. | Stakeholder perspective summary; archive LifeX pain points. | Open
P05 | Platform boundary is unclear between TSF and Cognite | Platform positioning | Data Platforms | David Teixugueira-de-Castro: TSF must be positioned inside the data-platform reference model; archive notes management hears conflicting messages. | Cognite programme, modelers, data officers, platform architects | Cognite is framed as an operational graph while TSF is framed as formal semantic authority, but the integration boundary is not explicit enough. | Platform discussions turn into competition instead of a layered architecture. | Cognite contextualization proceeds while semantic governance remains adjacent. | Define TSF as the governed meaning layer consumed by Cognite for LifeX-relevant equipment classes, mappings, and rules. | High | 0-60 days | Cognite programme lead and TSF semantic authority | TSF-to-Cognite mapping pattern agreed for priority LifeX classes and source identifiers. | Stakeholder profile; FAQ platform positioning. | Open
P06 | Manual mapping absorbs delivery effort | Data modeling and mapping | Data Platforms | Bastien Jouret: semantic work matters when it removes manual mapping and supports real use cases. | Modelers, data engineers, business analysts | Source descriptions, tags, standards, and local naming conventions are not aligned through reusable semantic mappings. | Teams spend project time reconciling concepts instead of delivering decision outputs. | Manual mapping and project-specific translation between source data and business terms. | Use TSF mappings to translate non-aligned object descriptions into governed equipment and process concepts. | High | 30-90 days | Data modeling lead with TSF modelers | Reduction in duplicated mappings; priority LifeX equipment families mapped once and reused by consuming platforms. | Stakeholder profile; executive deck problem slide. | Open
P07 | Conceptual model knowledge is lost in implementation | Data modeling and knowledge capture | Standards and Innovation | Josephine Boulanger: conceptual models capture business meaning before it is flattened into implementation artifacts. | Data modelers, business SMEs, data product teams | Business-led conceptual modeling is not always preserved as an explicit semantic asset with ownership and reuse path. | Business meaning is lost when delivery ends as SQL-like schemas, local documents, or platform-specific models. | Business knowledge is reconstructed during each project or held by individual modelers. | Capture conceptual models as TSF assets with business definitions, mappings, validation status, and consumer links. | Medium | 30-90 days | Data exposure and semantic modeling teams | Conceptual model assets linked to TSF concepts and platform outputs for priority use cases. | Stakeholder profile. | Open
P08 | Collibra and TSF perimeter is not explicit | Governance and catalog | Data Platforms | Francois-Xavier Mourot: perimeter between catalog governance and semantic modeling has to be clear. | Catalog owners, data stewards, semantic modelers, data domains | Collibra governs data assets and lineage while TSF governs semantic definitions, but handoffs are not formalized. | Data catalog terms can diverge from semantic definitions, creating parallel governance vocabularies. | Catalog and semantic workstreams advance separately with ad hoc mapping. | Connect Collibra entries to TSF concepts, with clear ownership, lineage, approval, and change-management rules. | High | 30-90 days | Collibra owner and TSF semantic authority | Priority Collibra business objects reference TSF concept IDs and semantic owners. | Stakeholder profile; FAQ Collibra positioning. | Open
P09 | Governance metrics are not yet practical enough | Governance and adoption | Data Platforms | Sonia Vallejo-Vaca: semantic governance must be practical, measurable, and connected to search, EDM, Cognite, and AI agents. | Data strategy, governance teams, platform teams, AI roadmap owners | Semantic governance is not yet translated into operating metrics that platform and AI teams can manage. | Governance remains a principle rather than a management system for reuse, quality, and AI readiness. | Teams discuss governance maturity without a consistent scorecard tied to outputs. | Track semantic asset coverage, platform integration rate, reuse rate, drift issues, audit completeness, and decision package traceability. | High | 30-90 days | Data strategy and governance office | Monthly semantic governance dashboard defined and piloted on LifeX. | Stakeholder profile; executive deck operating model. | Open
P10 | Affiliate data ownership and quality are uneven | Source data readiness | Data Platforms | Pascal Colombani: source ownership, DMP completeness, and quality controls are prerequisites for scaling semantic outputs. | EP data officers, affiliate data owners, platform teams | Data Management Plans, ownership, and data quality maturity vary across affiliates and domains. | Semantic outputs cannot scale reliably if source systems and owners are unclear. | Local remediation before dashboarding or executive reporting. | Tie semantic assets to source-system owners, DMP completeness, quality rules, and readiness criteria before scaling. | Medium | 30-90 days | EP data office with affiliate owners | LifeX source inventory includes owner, quality status, semantic mapping status, and readiness rating. | Stakeholder profile. | Open
P11 | AI teams cannot easily consume ontology assets | AI and API consumption | AI, Search and Operations | Elie Maze: AI teams need semantic assets through usable APIs; archive notes ontology data is not accessible via API today. | AI teams, data scientists, Mistral / LLM users, platform engineers | Semantic assets are not packaged as queryable services that AI pipelines can call. | AI work relies on local prompts, retrieval, and data preparation instead of governed concepts and provenance. | Ad hoc collaboration with semantic experts or local copies of vocabulary. | Expose TSF concepts, mappings, and LifeX semantic graph slices through APIs or query endpoints for AI workflows. | High | 30-90 days | AI platform team and TSF technical owner | First AI workflow consumes TSF concepts through an agreed API or query endpoint. | Stakeholder profile; FAQ AI readiness. | Open
P12 | Search quality depends on weak vocabulary and metadata foundations | Search and document grounding | AI, Search and Operations | Pierre Jallais: search quality depends on vocabulary, metadata, and discoverable semantic resources. | Search team, document owners, data stewards, operational users | Controlled vocabularies and metadata quality are not consistently available at document source. | RAG and enterprise search return relevant text but may miss governed definitions, equipment context, or decision impact. | Search teams compensate with local taxonomies, metadata fixes, and prompt design. | Publish discoverable TSF vocabularies and LifeX concept mappings for search indexing and RAG grounding. | Medium | 30-90 days | Search owner with semantic governance | Search index includes priority TSF vocabulary terms and LifeX aliases; relevance tested on signed questions. | Stakeholder profile; FAQ RAG and SKG positioning. | Open
P13 | Business impact model is incomplete | Business value and ROI | All layers | Archive states semantic graphs need stronger realizable impact modeling for OPEX, CAPEX, revenue, safety, and risk. | Management sponsors, LifeX owner, TSF modelers, finance / planning teams | Ontology assets do not yet make enough business impacts explicit for decision makers. | Leadership cannot see how semantic work changes investment, safety, production, or risk choices. | Benefits are described qualitatively or through broad hypotheses. | Model LifeX impacts as first-class semantic objects: cost, schedule, safety, production, integrity, risk, and decision rationale. | Critical | 0-60 days | LifeX owner, TSF modelers, finance / planning input | Each priority LifeX decision question links to at least one impact object and one source-evidence chain. | Archive executive findings; use case showcase. | Open
P14 | Operating model for semantic delivery is not explicit | Operating model | All layers | Archive quote: semantics will not be heard until the operating model question is answered. | TSF team, domain SMEs, platform teams, governance teams | Roles are not yet formalized across central semantic authority, domain contributors, and platform consumers. | Semantic work remains expert-led and hard to scale beyond individual champions. | Local coordination and informal handoffs between semantic experts and platform teams. | Define central meaning, domain knowledge capture, platform consumption, drift monitoring, and approval workflows. | High | 0-60 days | OneTech data governance with TSF sponsor | Operating model signed for LifeX semantic data product, including RACI and change process. | Archive operating model slide; executive deck operating model. | Open
P15 | Industrialization path after LifeX is not packaged | Scaling and industrialization | Operations and Business | Julien Campan profile frames LifeX as a blueprint that should scale through the Digital Factory once proven. | LifeX owner, Digital Factory, asset teams, platform teams | The scale path from pilot to production to other assets is not described as a repeatable package. | A successful LifeX effort could remain local instead of becoming a reusable enterprise pattern. | Pilot knowledge is transferred through meetings and project artifacts. | Package LifeX semantic data product as a repeatable blueprint with scope, mappings, APIs, governance, metrics, and onboarding steps. | Medium | 60-120 days | LifeX owner with Digital Factory and TSF | Reusable LifeX blueprint created and assessed for one next asset or equipment family. | Stakeholder profile; use case showcase. | Open
P16 | Evidence traceability is weak across decision packages | Decision traceability | Operations and Business | Executive deck and use case showcase emphasize field evidence to decision rationale as the LifeX target chain. | LifeX owner, inspectors, management reviewers, data product teams | Evidence, concepts, rules, and decision rationale are not linked in one auditable chain. | Management decisions take longer to prepare and are harder to defend or reuse across FPSOs. | Analysts manually reconcile reports, dashboards, spreadsheets, and memos. | Build traceability from observation to equipment concept, rule, source evidence, risk / cost impact, and recommendation. | Critical | 0-60 days | LifeX data product owner and semantic modelers | A management decision package can show traceable links from evidence to recommendation for one priority scenario. | Use case showcase; stakeholder summary. | Open